## 1 Tanmay (Lab)
Tanmay: Lab stream
Set Done to Yes when the task is finished (tests passed). Edited by hand.
Done
Task | Sprint | Task title | Done
L-01 | 1 | Repository skeleton and tooling run end to end (tracer bullet) | No
L-02 | 1 | Instance contract v0 (IF-6) | No
L-03 | 1 | Instance event schema (IF-4), app-event names and fake ingest | No
L-04 | 1 | Orchestrator API (IF-5), InstanceHost protocol and fake orchestrator | No
L-05 | 1 | Lab fragment of the platform API (IF-2) with a mock | No
L-06 | 1 | Stub shop, fake ingest and lab harness | No
L-07 | 1 | Contract checks live in CI | No
L-08 | 1 | Oracle account, two VMs, private link and firewall | No
L-09 | 2 | Tag contracts v1.0.0 and start the change rules | No
L-10 | 2 | DuckDNS names and certificates | No
L-11 | 2 | Vercel project, same-origin rewrite and live-stream check | No
L-12 | 2 | Image builds for amd64 and arm64 and deploy pipelines | No
L-13 | 2 | Orchestrator creates an instance from a template | No
L-14 | 2 | Reset, teardown, timing defaults and reconciler | No
L-15 | 2 | Instance isolation and hardening | No
L-16 | 2 | Concurrency, quotas, start failures and warm-pool decision | No
L-17 | 3 | Edge and gate for instance access | No
L-18 | 3 | Event relay, ingest and one active browser session | No
L-19 | 3 | Flag derivation, injection and secrecy | No
L-20 | 3 | Coraza sidecar, automatic capture and paste | No
L-21 | 3 | Milestone engine and evidence capture | No
L-22 | 3 | Attempt state machine and server clock | No
L-23 | 3 | Scoring engine | No
L-24 | 3 | Backups, laptop fallback and remaining spikes | No
L-25 | 4 | Time metrics, event log and sharing signal | No
L-26 | 4 | Reset and withdrawal during an assessment | No
L-27 | 4 | Anti-cheat signals and held-capture review | No
L-28 | 4 | Cohort board and ranking aid | No
L-29 | 4 | Isolation proof and extra hardening on VM-I | No
L-30 | 4 | End-to-end suite and load check | No
L-31 | 4 | Demo rehearsal and submission pack | No

## 2 Akshay (Platform)
Akshay: Platform stream
Set Done to Yes when the task is finished (tests passed). Edited by hand.
Done
Task | Sprint | Task title | Done
P-01 | 1 | Platform stack runs end to end locally (tracer bullet) | No
P-02 | 1 | Error registry and problem-details format (IF-8) | No
P-03 | 1 | Domain event schema (IF-3) with fixtures and replay script | No
P-04 | 1 | Platform and lab API fragments, bundle, mock and generated clients (IF-1, IF-2) | No
P-05 | 1 | Ports, in-memory fakes and table ownership (IF-9, IF-10) | No
P-06 | 1 | API skeleton: kernel and single-head migrations | No
P-07 | 1 | Dashboards skeleton with the same-origin proxy (local) | No
P-08 | 1 | Sign off contracts v1.0.0 as provider and consumer | No
P-09 | 2 | Outbox, queue worker and email provider | No
P-10 | 2 | Email templates and in-app warnings | No
P-11 | 2 | Learner signup, email verification and signup abuse protection | No
P-12 | 2 | Login, sessions, timeouts and CSRF | No
P-13 | 2 | Account types, candidate role and admin creation | No
P-14 | 2 | Password reset, password quality and account self-service | No
P-15 | 2 | Multi-factor login | No
P-16 | 2 | Consent screen, consent record, minimum data and 18-and-over | No
P-17 | 3 | Audit log and key service | No
P-18 | 3 | Recruiter signup and company approval | No
P-19 | 3 | Company members, admin controls, data scoping, terms and invite caps | No
P-20 | 3 | Assessment template, creating and sending invites, invite lifecycle | No
P-21 | 3 | Accepting invites, re-invite after a fault and bulk invites | No
P-22 | 3 | Live updates hub: SSE, heartbeat, snapshot with polling fallback, fan-out | No
P-23 | 3 | Stream authorisation and HTTP/2 | No
P-24 | 3 | Retention scheduler, retention rules and log rules | No
P-25 | 4 | Deletion workflow, 7-day undo and "who viewed me" | No
P-26 | 4 | Learner and candidate dashboards with hints | No
P-27 | 4 | Recruiter dashboard, live monitor and hints used | No
P-28 | 4 | Admin operations: queue, users, force-stop, settings, quotas, capacity | No
P-29 | 4 | Data exports | No
P-30 | 4 | Admin dashboard and privacy wall in every view | No
P-31 | 4 | Break-glass, audit access, admin limits, legal review and incident handling | No
P-32 | 4 | Deployed verification and ASVS checklist | No

## 3 Sahil (Target)
Sahil: Target stream
Set Done to Yes when the task is finished (tests passed). Edited by hand.
Done
Task | Sprint | Task title | Done
T-01 | 1 | Shop skeleton runs in a container (tracer bullet) | No
T-02 | 1 | Challenge catalogue schema and 11 stub entries (IF-7) | No
T-03 | 1 | Review the instance contract and event schema as consumer | No
T-04 | 1 | Shop skeleton meets the instance contract in the lab harness | No
T-05 | 1 | Exploit test runner skeleton | No
T-06 | 1 | Shop data model and seven state machines | No
T-07 | 1 | Shop identity, six roles, permissions and strong hashing | No
T-08 | 1 | Snapshot seeding mechanism | No
T-09 | 2 | Health, readiness after the injector marker and runtime profile | No
T-10 | 2 | Shop boundaries and signed app events | No
T-11 | 2 | Mock services container | No
T-12 | 2 | Isolated import service | No
T-13 | 2 | Support-agent bot | No
T-14 | 2 | Customer flows | No
T-15 | 2 | Support, finance and admin flows | No
T-16 | 2 | Seeded accounts for the challenges | No
T-17 | 3 | Seller flows | No
T-18 | 3 | Refunds, disputes, commissions and payouts | No
T-19 | 3 | C01 Broken Access Control (cross-store order read) | No
T-20 | 3 | C02 Cryptographic Failures (gift-card codes from a weak hash) | No
T-21 | 3 | C03 Injection (SQL injection and stored XSS) | No
T-22 | 3 | C04 Insecure Design (refund total beyond the amount paid) | No
T-23 | 3 | C05 Security Misconfiguration (unauthenticated diagnostics page) | No
T-24 | 3 | C06 Vulnerable Components (prototype pollution in the import service) | No
T-25 | 4 | C07 Authentication Failures (weak password-reset code) | No
T-26 | 4 | C08 Software or Data Integrity Failures (unsigned payment webhook) | No
T-27 | 4 | C09 Logging and Alerting Failures (legacy login route not logged) | No
T-28 | 4 | C10 Server-Side Request Forgery (seller image import) | No
T-29 | 4 | C11 Mishandling of Exceptional Conditions (KYC check fails open) | No
T-30 | 4 | Catalogue content: tags, tiers, briefs, hints, write-ups and decoy locations | No
T-31 | 4 | Cross-challenge tests and exploit tests as a CI release gate | No
T-32 | 4 | Deployed verification on the instance VM | No